Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

| Date | 17 September 2026 |
| --- | --- |
| Team ID | Individual project |
| Project Name | Employee Issue Management – Record Producer and Service Portal Integration |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation

The product backlog below breaks the ServiceNow Employee Issue Management project into functional requirements (epics), user stories, story points, priority, and sprint allocation. As this is an individual project, the work is planned across four sprints covering employee issue submission, validation, issue management, tracking, testing, and documentation.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Employee Issue Submission | USN-1 | As an employee, I can access the Raise an Employee Issue functionality through the Service Portal. | 2 | High |
| Sprint-1 | Employee Issue Submission | USN-2 | As an employee, I can provide the required issue details through the Record Producer before submitting an issue. | 1 | High |
| Sprint-1 | Issue Record Creation | USN-3 | As an employee, I can submit an issue and have an Employee Issue record created in the custom table. | 1 | High |
| Sprint-1 | Issue Record Creation | USN-4 | As an employee, I can view the submitted issue and identify its current processing status. | 1 | Medium |
| Sprint-2 | Validation & Field Behavior | USN-5 | As an employee, I can receive validation for required and invalid field values before submitting an issue. | 2 | High |
| Sprint-2 | Validation & Field Behavior | USN-6 | As an employee, I can see relevant field behavior based on my selections through UI Policies and field dependencies. | 2 | High |
| Sprint-2 | Server-side Validation | USN-7 | As the system, I can validate and process submitted Employee Issue records using server-side business logic. | 1 | High |
| Sprint-3 | Issue Assignment & Prioritization | USN-8 | As a support team member, I can receive an Employee Issue assigned to the appropriate assignment group. | 2 | High |
| Sprint-3 | Issue Assignment & Prioritization | USN-9 | As a support team member, I can use the configured issue information to determine and manage issue priority. | 2 | High |
| Sprint-3 | Issue Management | USN-10 | As a support team member, I can update the issue status while working toward resolution. | 1 | Medium |
| Sprint-4 | Testing & Monitoring | USN-11 | As an administrator, I can test the complete employee issue submission and management process using the Service Portal. | 2 | High |
| Sprint-4 | Testing & Monitoring | USN-12 | As an administrator, I can verify client-side validation, field dependencies, and server-side business rules. | 1 | Medium |
| Sprint-4 | Documentation | USN-13 | As an administrator/project owner, I can document the application configuration, issue workflow, components, and expected outcomes. | 1 | Medium |

The backlog is divided across four sprints so that the employee-facing submission process, validation, issue-management functionality, and final testing/documentation are completed in a logical sequence.

Project Tracker, Velocity & Burndown Chart:

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 5 | 6 Days | 25 Aug 2026 | 30 Aug 2026 | 5 | 30 Aug 2026 |
| Sprint-2 | 5 | 6 Days | 31 Aug 2026 | 05 Sep 2026 | 5 | 05 Sep 2026 |
| Sprint-3 | 5 | 6 Days | 06 Sep 2026 | 11 Sep 2026 | 5 | 11 Sep 2026 |
| Sprint-4 | 5 | 6 Days | 12 Sep 2026 | 17 Sep 2026 | 5 | 17 Sep 2026 |

Velocity:

The template defines velocity as a measure of the amount of work completed during an iteration. For this individual project, the planned average velocity is calculated from the planned story points and sprint duration.

Average velocity per day = Total planned story points ÷ Total planned project days

= 20 ÷ 24

= 0.83 story points/day

The planned sprint velocity is:

5 story points per 6-day sprint ≈ 0.83 story points/day

Therefore, the project maintains a planned velocity of approximately 0.83 story points per day, or 5 story points per sprint.

Burndown Chart:

A burndown chart represents the amount of work remaining over time. For this project, the planned remaining story points decrease as each sprint is completed:

Sprint-wise Work Summary:

Sprint-1: Employee Issue Submission

Set up the Service Portal entry point, Raise an Employee Issue functionality, Record Producer, required issue fields, and Employee Issue custom table. Implement the basic submission process and verify that submitting the Record Producer creates an Employee Issue record.

Sprint-2: Validation & Field Dependencies

Configure Client Scripts, UI Policies, Data Policies, and field dependencies. Implement required-field validation, valid input handling, dynamic field behavior, and server-side validation through Business Rules.

Sprint-3: Assignment, Prioritization & Issue Management

Configure the issue-management logic for assignment and prioritization. Implement the appropriate business rules and support-team handling. Enable issue status updates so that submitted issues can progress through the management and resolution process.

Sprint-4: Testing & Documentation

Perform end-to-end testing of the Service Portal → Record Producer → Employee Issue Table flow. Verify validation, field dependencies, Business Rules, assignment, prioritization, and status tracking. Test different issue scenarios and complete the project architecture, configuration, implementation, and user documentation.